## Sheet1
Phase | Task Description | Expected Duration | Timeline
Phase 1: Project Planning | Define project scope, objectives, and deliverables. | 1 | 1
Phase 2: Data Collection | Gather book data and user preferences from external APIs and public datasets. | 2 | 3
Phase 3: Data Preprocessing | Clean, format, and preprocess collected data. Handle missing data and text vectorization. | 2 | 5
Phase 4: Model Development | Implement collaborative and content-based filtering models. Build hybrid recommendation engine. | 3 | 8
Phase 5: Front-End Development | Design and implement the user interface for search, rating, and recommendation display. | 2 | 10
Phase 6: Integration | Integrate the front-end with the back-end, connecting the recommendation engine to the UI. | 2 | 12
Phase 7: Testing and Evaluation | Test the system for performance, accuracy, and usability. Refine recommendation algorithms based on feedback. | 2 | 14
Phase 8: Deployment | Deploy the system on cloud infrastructure, ensuring scalability and accessibility. | 1 | 15
Phase 9: Documentation | Finalize project documentation, user manual, and future work suggestions. | 1 | 16
Total Duration |  | 16